## Schedule Calculator
DISCLAIMER: this schedule shows a many possible steps with "very conservative" timelines in each. Projects can eliminate steps and adjust timelines as needed.
A typical Simplar XPD project can go much faster than shown and is always customized to meet project-specific needs.
Key:
| Project: | Insert Name Here |  |  |  |  | Only update the green cells
| When do we expect the SOW to be completed? | 2021-06-15
1) Planning Phase (Develop SOW + RFN + RFP) |  | Date | Duration (days) | Duration (weeks) | Duration (months) | Comments
1 | Planning Meeting with Procurement / Supply Chain | 2021-06-07 | 30 | 4.2857 | 0.98361
2 | Compile the Statement of Work (SOW) | 2021-06-08 | 1 | 0.14286 | 0.032787 | assumes ~1mo to compile the SOW
3 | Full SOW is ready for release | 2021-06-15 | 7 | 1 | 0.22951 | assumes ~1 week compilation before advertise
4 | Request for Needs (RFN) - advertise to vendors & hold Info Session | 2021-06-15 | 0 | 0 | 0 | advertise the RFN once SOW is ready
5 | Request for Needs (RFN) - vendor responses are due | 2021-07-06 | 21 | 3 | 0.68852 | ~1-2wk small projects and 2-3wks larger/complex projects
6 | Final Scope Preparation (update based on Vendor feedback) | 2021-08-05 | 30 | 4.2857 | 0.98361 | assumes ~1mo to update/finalize SOW
|  | Total: | 89 | 12.7143 | 2.918
2) Selection Phase (Solicit & Evaluate Proposals) |  | Date | Duration (days) | Duration (weeks) | Duration (months) | Comments
1 | RFP(s) released to vendors | 2021-08-12 | 7 | 1 | 0.22951
2 | Pre-Proposal Information Session(s) / Site Walk | 2021-08-19 | 7 | 1 | 0.22951 | schedule for roughly 1 wk after RFP release
3 | Vendor proposals are due | 2021-09-12 | 24 | 3.4286 | 0.78689 | assumes ~4-5wk for proposal response
4 | Evaluate vendor written proposals | 2021-09-26 | 14 | 2 | 0.45902 | can go as fast as evaluators are available
5 | Lead time for Intervires and/or Product Demos | 2021-10-06 | 10 | 1.4286 | 0.32787 | give 1-2wk notice for SL vendors to attend Int/Demos
6 | Interviews and/or Product Demonstrations | 2021-10-13 | 7 | 1 | 0.22951 | assumes 1wk window for Int/Demos
7 | Final Selection Results | 2021-10-15 | 2 | 0.28571 | 0.065574 | should be quick to assemble!
8 | Internal approvals & executive briefings | 2021-10-29 | 14 | 2 | 0.45902 | depends on internal approvals process
|  | Total: | 85 | 12.1429 | 2.7869
3) Execute Contract (clarification & negotiation) |  | Date | Duration (days) | Duration (weeks) | Duration (months) | Comments
1 | Notification & Preparation | 2021-11-05 | 7 | 1 | 0.22951 | 1 wk to orient, train, and prep
2 | Clarification Kickoff Meeting(s) | 2021-11-12 | 7 | 1 | 0.22951 | 1wk window for Kickoff Meeting
3 | Clarification Activities - detailed planning & documentation | 2021-12-12 12:00 | 30.5 | 4.3571 | 1 | highly variable…
4 | Clarification Summary Meeting(s) | 2021-12-19 12:00 | 7 | 1 | 0.22951 | 1wk window
5 | Contract Signature | 2021-12-21 12:00 | 2 | 0.28571 | 0.065574 | work on contract in parallel with clarification!!!
6 | Notice to Proceed | 2021-12-23 12:00 | 2 | 0.28571 | 0.065574 | how quickly should vendors expect to mobilize?
|  | Total: | 55.5 | 7.9286 | 1.8197 | driven by internal W&R SME availability & # vendors
Formulas:
Insert Name Here = [Insert Name Here, row below]-[Duration (days), row below]
Insert Name Here = [Insert Name Here, row above]+[Duration (days)]